## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Mahashri Balakrishnan | 2025-12-08 | Unused imports were not being detected correctly for certain Python files | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports | 2025-12-09 | Closed | Issue resolved and validated with sample programs
2 | Mahashri Balakrishnan | 2025-12-09 | PEP8 style violations were not highlighted consistently in the output | Sprint 1 | Self | Standards | Integrated stricter PEP8 checks and improved formatting rules | 2025-12-11 | Closed | Style detection accuracy improved
3 | Mahashri Balakrishnan | 2026-01-15 | Error detection module missed syntax errors in nested blocks | Sprint 2 | Self | Logical | Enhanced AST parsing and added deeper recursion checks | 2026-02-17 | Closed | Error detection accuracy improved
4 | Mahashri Balakrishnan | 2026-02-17 | Code score calculation was inconsistent for similar inputs | Sprint 3 | Self | Logical | Refined scoring algorithm and added weighted evaluation metrics | 2026-02-19 | Closed | Scoring consistency improved
5 | Mahashri Balakrishnan | 2026-03-21 | History feature not saving previous code reviews | Sprint 3 | Self | Logical | Implemented local storage/database integration for history tracking | 2026-03-25 | Closed | History feature functioning correctly

## Sheet2
Logical
User Interface
Maintainability
Standards
Others